## project
Project Planner
[6 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Build Bibliographic Network | 1 | 1 |  | 4 | 25%
Clean Data | 1 | 1 |  | 6 | 100%
Explore Dataset | 1 | 2 |  |  | 35%
Reproduce Work of Valverde et. al. | 3 | 2 |  |  | 10%
Analyse Technology Codes | 5 | 1
Build Text Similarilty Network | 4 | 1 |  |  | 85%
Extend Model using addition features | 5 | 2 |  |  | 85%
Explore Predictability | 7 | 2 |  |  | 50%
Write Up | 9 | 2 |  |  | 60%
Activity 09 | 5 | 2 |  |  | 75%
Activity 10 | 6 | 5 |  |  | 100%
Activity 11 | 6 | 1 |  |  | 60%
Activity 12 | 9 | 3 |  |  | 0%
Activity 13 | 9 | 6 |  |  | 50%
Activity 14 | 9 | 3 |  |  | 0%
Activity 15 | 9 | 4 |  |  | 1%
Activity 16 | 10 | 5 |  |  | 80%
Activity 17 | 11 | 2 |  |  | 0%
Activity 18 | 12 | 6 |  |  | 0%
Activity 19 | 12 | 1 |  |  | 0%
Activity 20 | 14 | 5 |  |  | 0%
Activity 21 | 14 | 8 |  |  | 44%
Activity 22 | 14 | 7 |  |  | 0%
Activity 23 | 15 | 4 |  |  | 12%
Activity 24 | 15 | 5 |  |  | 5%
Activity 25 | 15 | 8 |  |  | 0%
Activity 26 | 16 | 28 |  |  | 50%

## GANTT
GANTT CHART |  |  | Week
Activity | Week Start | Week End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | …
Clean Data | 1 | 2
Explore Dataset | 1 | 3
Build Bibliographic Network | 2 | 3
Reproduce Work of Valverde et. al. | 3 | 5
Explore Text Data | 4 | 5
Analyse Technology Codes | 6 | 7
Build Text Similarilty Network | 5 | 6
Extend Model using addition features | 7 | 9
Explore Predictability | 9 | 11
Write Up | 11 | END
Critical Activity
Desired Activity

## PERT
[12 empty] | Name | Explore Predictibility |  |  | Name | Write Up
Name | Clean Data | [10 empty] | Start Week | 9 | Duration | 2 | Start Week | 11 | Duration
Start Week | 1 | Duration | 1 | [8 empty] | Finish Week | 11 | Note | Milestone | Finish Week | END | Note
Finish Week | 2 | Note
Name | Build Bibliographic Network |  |  | Name | Reproduce Work | [6 empty] | Name | Extend Model
Start Week | 2 | Duration | 1 | Start Week | 3 | Duration | 2 |  |  |  |  | Start Week | 7 | Duration | 2
Finish Week | 3 | Note | MileStone | Finish Week | 5 | Note | Milestone |  |  |  |  | Finish Week | 9 | Note | Milestone
Name | Explore Data |  |  | Name | Explore Text Data |  |  | Name | Build Text Similarity Network
Start Week | 1 | Duration | 2 | Start Week | 4 | Duration | 1 | Start Week | 5 | Duration | 2
Finish Week | 3 | Note |  | Finish Week | 5 | Note |  | Finish Week | 7 | Note
[8 empty] | Name | Extract Technology Codes and other features
| Critical Path |  | Desired Path |  |  |  |  | Start Week | 6 | Duration | 1
[8 empty] | Finish Week | 7 | Note